## Scope Schedule
Scope Item | Location / Entity | Qty | Owner / Vendor Responsibility | Authority Source | Parser Stress | Expected Packet
Cat6A cabling for AP locations | Durkin Admin Building | 48 | Vendor furnishes/install cabling only | Specifications and Drawings | synthetic count; AP device itself excluded | scope_inclusion
Wireless Access Points | Durkin Admin Building | 48 | WPS IT provides - DO NOT QUOTE | Specifications and Drawings | owner-furnished equipment exclusion | scope_exclusion
Existing copper re-termination | MDF and IDF rooms | 220 | Vendor re-terminates existing copper wiring | Addendum 1 Phase B | existing vs new work distinction | scope_inclusion
New keystone patch panels | MDF/IDF | 8 | Vendor furnishes/install | Addendum 1 Phase B | patch panel count vs port count | scope_inclusion
New 8U network cabinet | Basement IDF Room 010 | 1 | Vendor furnishes/install | Addendum 1 Phase B | IDF Room 010 must not merge with Room 101 | scope_inclusion
Faulty endpoint replacements | pre-determined endpoints | TBD | Vendor replaces pre-determined faulty endpoints | Addendum 1 Phase B | TBD quantity should become missing_info | missing_info
Label format | MDF/IDF patch panels | N/A | Vendor labels per room/panel/port format | Specifications and Drawings | labeling standard extraction | missing_info

## Risk Seeds
Risk ID | Risk Trigger | Evidence Source | Why PM Cares | Expected Family | Severity
WO-001 | Quote includes AP hardware, specs say WPS IT provides APs / DO NOT QUOTE | spec + quote | owner-furnished equipment mistakenly procured | scope_exclusion | critical
WO-002 | Addendum 1 adds Phase B copper re-termination | bid page + addendum | original specs-only parse would miss active scope | scope_inclusion | critical
WO-003 | Faulty endpoint count is TBD | addendum + quote | labor/material exposure unresolved | missing_info | high
WO-004 | IDF Room 010 and Room 101 are distinct | addendum + schedule | entity resolver false merge risk | entity_resolution | critical